## Sprint 1
Quarter 1 (Jan-Mar)
Sprint_1 Month_Jan
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
1 | 2023-01-01 | 2023-01-14 | 14 Days | Implement core user authentication and initial dashboard setup | 1000000 | 75000 | 100000 | 100000 | 0 | 75000 | 350000 | 100000 | 450000 | 5 | 22500 | 472500 | 550000 | 527500 | 1000000 | 1000000 | 13
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
1 | User Login | Allow users to log in securely | High | To Do | 5 | Sprint 1 | User can log in using email and password; proper error messages are shown. | Design UI, Implement authentication, Test login flow | None | Low | Requires UI review
2 | Dashboard Overview | Display summary of inventory and alerts | High | To Do | 8 | Sprint 1 | Dashboard displays key metrics and alerts in real time. | Layout design, Data integration, UI testing | User Login must be complete | Medium | Waiting for design input
`
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-01-01 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-02 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-01-03 | Tuesday | 1 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Absent | 0
2023-01-04 | Wednesday | 1 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-05 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Absent | 0
2023-01-06 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-01-07 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-08 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-09 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Absent | 0
2023-01-10 | Tuesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-11 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-12 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-13 | Friday | 2 | Present | 8 | Absent | 0 | Present | 8 | Present | 8 | Present | 8
2023-01-14 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 9 | 1
Python Dev 1 | 9 | 1
Python Dev 2 | 10 | 0
Tester | 7 | 3
Data Analyst | 7 | 3
Sprint Velocity
Metric | Value
Total Estimated Story Points | 13
Velocity (Story Points Completed) | 13
Story Points Tracking
Date | Remaining Story Points
2023-01-01 | 13.1
2023-01-02 | 12.2
2023-01-03 | 11.3
2023-01-04 | 10.3
2023-01-05 | 9.1
2023-01-06 | 8.2
2023-01-07 | 7.7
2023-01-08 | 6.5
2023-01-09 | 5.3
2023-01-10 | 4.9
2023-01-11 | 3.6
2023-01-12 | 2.7
2023-01-13 | 1.8
2023-01-14 | 1
2023-01-15 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 1 | Team collaboration was excellent | Need to refine our process | Schedule daily stand-ups

## Sprint 2
Sprint_2 Month_Jan
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
2 | 2023-01-15 | 2023-01-28 | 14 Days | Develop sales processing and stock refill functionalities | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 14.5
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
3 | Sell Medicine Feature | Record medicine sales with validation | High | To Do | 8 | Sprint 2 | Sales can be recorded with proper validation and error handling. | Design sale form, Implement validation, Integrate with DB | Dashboard Overview | High | Confirmed with client
4 | Refill Stock Feature | Update stock levels and add new medicines | High | To Do | 8 | Sprint 2 | Stock levels update correctly and new medicines are added. | Design stock update module, Develop refill logic, Testing | Sell Medicine Feature | Medium | Confirmed with client
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-01-15 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-16 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-17 | Tuesday | 1 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-18 | Wednesday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-19 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-20 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-21 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-22 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-23 | Monday | 2 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-01-24 | Tuesday | 2 | Absent | 0 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-01-25 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-26 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-01-27 | Friday | 2 | Absent | 0 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-01-28 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 7 | 3
Python Dev 1 | 10 | 0
Python Dev 2 | 9 | 1
Tester | 7 | 3
Data Analyst | 10 | 0
Sprint Velocity
Metric | Value
Total Estimated Story Points | 16
Velocity (Story Points Completed) | 14.5
Story Points Tracking
Date | Remaining Story Points
2023-01-15 | 16.6
2023-01-16 | 15.3
2023-01-17 | 13.3
2023-01-18 | 12.2
2023-01-19 | 12
2023-01-20 | 10.1
2023-01-21 | 8.7
2023-01-22 | 8.4
2023-01-23 | 6.6
2023-01-24 | 5.9
2023-01-25 | 4.5
2023-01-26 | 3.6
2023-01-27 | 2.4
2023-01-28 | 1.1
2023-01-29 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 2 | All tasks were completed on time | Need to refine our process | Highlight the risk during sprint refirement

## Sprint 3
Sprint_3 Month_Feb
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
3 | 2023-01-29 | 2023-02-11 | 14 Days | Integrate low stock alerts and notification system | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 12.3333
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
5 | Low Stock Alerts | Automatically flag items below reorder level | Medium | To Do | 8 | Sprint 3 | Alerts are triggered when stock falls below threshold. | Define thresholds, Implement alert mechanism, Test alerts | Refill Stock Feature | Low | Pending further discussion
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-01-29 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-01-30 | Monday | 1 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-01-31 | Tuesday | 1 | Present | 8 | Absent | 0 | Present | 8 | Present | 8 | Present | 8
2023-02-01 | Wednesday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-02 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-02-03 | Friday | 1 | Present | 8 | Absent | 0 | Present | 8 | Present | 8 | Present | 8
2023-02-04 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-05 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-06 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-07 | Tuesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-08 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-09 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-10 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-11 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 9 | 1
Python Dev 1 | 8 | 2
Python Dev 2 | 10 | 0
Tester | 9 | 1
Data Analyst | 10 | 0
Sprint Velocity
Metric | Value
Total Estimated Story Points | 8
Velocity (Story Points Completed) | 12.3333
Story Points Tracking
Date | Remaining Story Points
2023-01-29 | 8.3
2023-01-30 | 7.3
2023-01-31 | 6.9
2023-02-01 | 6.2
2023-02-02 | 6
2023-02-03 | 5.2
2023-02-04 | 4.4
2023-02-05 | 4
2023-02-06 | 3.4
2023-02-07 | 2.7
2023-02-08 | 2.3
2023-02-09 | 1.7
2023-02-10 | 1.1
2023-02-11 | 0.6
2023-02-12 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 3 | Team collaboration was excellent | Need to refine our process | Review task estimates

## Sprint 4
Sprint_4 Month_Feb
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
4 | 2023-02-12 | 2023-02-25 | 14 Days | Create reporting modules for sales and inventory | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 11.25
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
6 | Reporting Module | Generate sales and inventory reports | Medium | To Do | 8 | Sprint 4 | Reports are accurate and exportable in PDF/Excel. | Design report templates, Code report generation, Validate data | Dashboard Overview, Low Stock Alerts | High | Pending further discussion
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-02-12 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-13 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-14 | Tuesday | 1 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-02-15 | Wednesday | 1 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-02-16 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-17 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-18 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-19 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-20 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-21 | Tuesday | 2 | Present | 8 | Absent | 0 | Present | 8 | Present | 8 | Present | 8
2023-02-22 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-23 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-24 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Absent | 0
2023-02-25 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 10 | 0
Python Dev 1 | 9 | 1
Python Dev 2 | 9 | 1
Tester | 9 | 1
Data Analyst | 9 | 1
Sprint Velocity
Metric | Value
Total Estimated Story Points | 8
Velocity (Story Points Completed) | 11.25
Story Points Tracking
Date | Remaining Story Points
2023-02-12 | 8.2
2023-02-13 | 7.3
2023-02-14 | 6.5
2023-02-15 | 6.2
2023-02-16 | 5.5
2023-02-17 | 5.4
2023-02-18 | 4.6
2023-02-19 | 4.1
2023-02-20 | 3.4
2023-02-21 | 2.9
2023-02-22 | 2.3
2023-02-23 | 1.7
2023-02-24 | 1.2
2023-02-25 | 0.5
2023-02-26 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 4 | Team collaboration was excellent | Need to refine our process | Highlight the risk in daily standup

## Sprint 5
Sprint_5 Month_Mar
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
5 | 2023-02-26 | 2023-03-11 | 14 Days | Implement user role management and access control | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 10.6
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
7 | User Role Management | Implement role-based access control | Low | To Do | 8 | Sprint 5 | Roles and permissions are configurable and secure. | Design role matrix, Implement RBAC logic, Test permissions | User Login | Medium | High priority follow-up needed
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-02-26 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-02-27 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-02-28 | Tuesday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-01 | Wednesday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-02 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-03 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-04 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-05 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-06 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-07 | Tuesday | 2 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-03-08 | Wednesday | 2 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Absent | 0
2023-03-09 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-03-10 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-11 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 9 | 1
Python Dev 1 | 10 | 0
Python Dev 2 | 9 | 1
Tester | 9 | 1
Data Analyst | 9 | 1
Sprint Velocity
Metric | Value
Total Estimated Story Points | 8
Velocity (Story Points Completed) | 10.6
Story Points Tracking
Date | Remaining Story Points
2023-02-26 | 7.7
2023-02-27 | 7.5
2023-02-28 | 6.7
2023-03-01 | 6
2023-03-02 | 5.7
2023-03-03 | 5.3
2023-03-04 | 4.7
2023-03-05 | 4.1
2023-03-06 | 3.5
2023-03-07 | 2.8
2023-03-08 | 2.2
2023-03-09 | 1.7
2023-03-10 | 1.1
2023-03-11 | 0.6
2023-03-12 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 5 | All tasks were completed on time | Communication gaps identified | work on team collaboration

## Sprint 6
Sprint_6 Month_Mar
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
6 | 2023-03-12 | 2023-03-25 | 14 Days | Enable data export functionality for inventory data | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 9.6667
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
8 | Data Export | Export inventory data to CSV/Excel | Low | To Do | 5 | Sprint 6 | Data exports correctly in chosen format. | Develop export functionality, Validate file format, User testing | Reporting Module | Low | Waiting for design input
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-03-12 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-13 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-14 | Tuesday | 1 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-15 | Wednesday | 1 | Present | 8 | Absent | 0 | Present | 8 | Present | 8 | Absent | 0
2023-03-16 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-17 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-18 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-19 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-20 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-21 | Tuesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-22 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-23 | Thursday | 2 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-24 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-25 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 8 | 2
Python Dev 1 | 9 | 1
Python Dev 2 | 10 | 0
Tester | 10 | 0
Data Analyst | 9 | 1
Sprint Velocity
Metric | Value
Total Estimated Story Points | 5
Velocity (Story Points Completed) | 9.6667
Story Points Tracking
Date | Remaining Story Points
2023-03-12 | 4.8
2023-03-13 | 4.8
2023-03-14 | 4.3
2023-03-15 | 4
2023-03-16 | 3.4
2023-03-17 | 3.1
2023-03-18 | 2.8
2023-03-19 | 2.4
2023-03-20 | 2
2023-03-21 | 1.9
2023-03-22 | 1.5
2023-03-23 | 1.1
2023-03-24 | 0.7
2023-03-25 | 0.3
2023-03-26 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 6 | Team collaboration was excellent | Some tasks took longer than expected | improve test cases to avoid bugs

## Sprint 7
Quarter 2 (Apr-Jun)
Sprint_7 Month_Apr
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
7 | 2023-03-26 | 2023-04-08 | 14 Days | Optimize application performance and scalability | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 9.4286
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
9 | Performance Optimization | Improve application speed and scalability | Medium | To Do | 8 | Sprint 7 | Application meets response time targets under load. | Profile application, Identify bottlenecks, Optimize code | Reporting Module, Data Export | High | Requires UI review
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-03-26 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-03-27 | Monday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-28 | Tuesday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-29 | Wednesday | 1 | Absent | 0 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-30 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-03-31 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-01 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-04-02 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-04-03 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-04 | Tuesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-05 | Wednesday | 2 | Absent | 0 | Absent | 0 | Present | 8 | Present | 8 | Present | 8
2023-04-06 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-07 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-08 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 8 | 2
Python Dev 1 | 9 | 1
Python Dev 2 | 10 | 0
Tester | 10 | 0
Data Analyst | 10 | 0
Sprint Velocity
Metric | Value
Total Estimated Story Points | 8
Velocity (Story Points Completed) | 9.4286
Story Points Tracking
Date | Remaining Story Points
2023-03-26 | 7.8
2023-03-27 | 7.6
2023-03-28 | 6.8
2023-03-29 | 6.3
2023-03-30 | 5.5
2023-03-31 | 4.9
2023-04-01 | 4.4
2023-04-02 | 4.1
2023-04-03 | 3.5
2023-04-04 | 3
2023-04-05 | 2.2
2023-04-06 | 1.7
2023-04-07 | 1.1
2023-04-08 | 0.6
2023-04-09 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 7 | Good client feedback | Some tasks took longer than expected | Review task estimates

## Sprint 8
Sprint_8 Month_Apr
Sprint Planning & Budget Allocation
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
8 | 2023-04-09 | 2023-04-22 | 14 Days | Conduct user training and finalize documentation | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 8.875
Product Backlog
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
10 | User Training | Prepare training guides and documentation | Low | To Do | 5 | Sprint 8 | Training materials are complete and user-friendly. | Draft guides, Record training sessions, Compile documentation | All previous sprints | Low | High priority follow-up needed
Team Attendance & Work Hours
Date | Day | Week | BA Attendance | BA Hours | Python Dev 1 Attendance | Python Dev 1 Hours | Python Dev 2 Attendance | Python Dev 2 Hours | Tester Attendance | Tester Hours | Data Analyst Attendance | Data Analyst Hours
2023-04-09 | Sunday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-04-10 | Monday | 1 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-04-11 | Tuesday | 1 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-04-12 | Wednesday | 1 | Present | 8 | Present | 8 | Absent | 0 | Present | 8 | Present | 8
2023-04-13 | Thursday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-14 | Friday | 1 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-15 | Saturday | 1 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-04-16 | Sunday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
2023-04-17 | Monday | 2 | Present | 8 | Present | 8 | Present | 8 | Absent | 0 | Present | 8
2023-04-18 | Tuesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-19 | Wednesday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-20 | Thursday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-21 | Friday | 2 | Present | 8 | Present | 8 | Present | 8 | Present | 8 | Present | 8
2023-04-22 | Saturday | 2 | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday | Holiday
Worker Attendance Summary
Worker | Present | Absent
BA | 10 | 0
Python Dev 1 | 10 | 0
Python Dev 2 | 7 | 3
Tester | 9 | 1
Data Analyst | 10 | 0
Sprint Velocity
Metric | Value
Total Estimated Story Points | 5
Velocity (Story Points Completed) | 8.875
Story Points Tracking
Date | Remaining Story Points
2023-04-09 | 4.9
2023-04-10 | 4.9
2023-04-11 | 4.4
2023-04-12 | 3.8
2023-04-13 | 3.7
2023-04-14 | 3.3
2023-04-15 | 3
2023-04-16 | 2.4
2023-04-17 | 2.2
2023-04-18 | 1.7
2023-04-19 | 1.5
2023-04-20 | 1.1
2023-04-21 | 0.7
2023-04-22 | 0.3
2023-04-23 | 0
Sprint Retrospective
Sprint | What Went Well | What Didn't Go Well | Action Items
Sprint 8 | All tasks were completed on time | Need to refine our process | Review task estimates

## Risk Register
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
2 | Dashboard Overview | Display summary of inventory and alerts | High | To Do | 8 | Sprint 1 | Dashboard displays key metrics and alerts in real time. | Layout design, Data integration, UI testing | User Login must be complete | Medium | Waiting for design input
3 | Sell Medicine Feature | Record medicine sales with validation | High | To Do | 8 | Sprint 2 | Sales can be recorded with proper validation and error handling. | Design sale form, Implement validation, Integrate with DB | Dashboard Overview | High | Confirmed with client
4 | Refill Stock Feature | Update stock levels and add new medicines | High | To Do | 8 | Sprint 2 | Stock levels update correctly and new medicines are added. | Design stock update module, Develop refill logic, Testing | Sell Medicine Feature | Medium | Confirmed with client
6 | Reporting Module | Generate sales and inventory reports | Medium | To Do | 8 | Sprint 4 | Reports are accurate and exportable in PDF/Excel. | Design report templates, Code report generation, Validate data | Dashboard Overview, Low Stock Alerts | High | Pending further discussion
7 | User Role Management | Implement role-based access control | Low | To Do | 8 | Sprint 5 | Roles and permissions are configurable and secure. | Design role matrix, Implement RBAC logic, Test permissions | User Login | Medium | High priority follow-up needed
9 | Performance Optimization | Improve application speed and scalability | Medium | To Do | 8 | Sprint 7 | Application meets response time targets under load. | Profile application, Identify bottlenecks, Optimize code | Reporting Module, Data Export | High | Requires UI review

## Retrospective Follow-up
Sprint | Action Items
Sprint 1 | Schedule daily stand-ups
Sprint 2 | Highlight the risk during sprint refirement
Sprint 3 | Review task estimates
Sprint 4 | Highlight the risk in daily standup
Sprint 5 | work on team collaboration
Sprint 6 | improve test cases to avoid bugs
Sprint 7 | Review task estimates
Sprint 8 | Review task estimates

## Dashboard
Metric | Value
Total Sprints | 8
Total Budget Allocated (Rs) | 8000000
Total Actual Cost (Rs) | 4125000
Total Revised Profit (Rs) | 3668750
Average Velocity (Story Points) | 7.6
Worker | Total Present | Total Absent
BA | 70 | 10
Python Dev 1 | 74 | 6
Python Dev 2 | 74 | 6
Tester | 70 | 10
Data Analyst | 74 | 6

## Total
Sprint Number | Sprint Start Date | Sprint End Date | Sprint Duration | Sprint Goal | Budget Allocated (Rs) | BA Salary (Rs) | Python Dev 1 Salary (Rs) | Python Dev 2 Salary (Rs) | Tester Salary (Rs) | Data Analyst Salary (Rs) | Total Salary Expense (Rs) | Operational Cost (Rs) | Total Cost (Rs) | Contingency (%) | Contingency Amount (Rs) | Revised Total Cost (Rs) | Profit (Rs) | Revised Profit (Rs) | Revenue (Rs) | Revised Revenue (Rs) | Velocity (Story Points Completed)
1 | 2023-01-01 | 2023-01-14 | 14 Days | Implement core user authentication and initial dashboard setup | 1000000 | 75000 | 100000 | 100000 | 0 | 75000 | 350000 | 100000 | 450000 | 5 | 22500 | 472500 | 550000 | 527500 | 1000000 | 1000000 | 13
2 | 2023-01-15 | 2023-01-28 | 14 Days | Develop sales processing and stock refill functionalities | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 14.5
3 | 2023-01-29 | 2023-02-11 | 14 Days | Integrate low stock alerts and notification system | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 12.3333
4 | 2023-02-12 | 2023-02-25 | 14 Days | Create reporting modules for sales and inventory | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 11.25
5 | 2023-02-26 | 2023-03-11 | 14 Days | Implement user role management and access control | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 10.6
6 | 2023-03-12 | 2023-03-25 | 14 Days | Enable data export functionality for inventory data | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 9.6667
7 | 2023-03-26 | 2023-04-08 | 14 Days | Optimize application performance and scalability | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 9.4286
8 | 2023-04-09 | 2023-04-22 | 14 Days | Conduct user training and finalize documentation | 1000000 | 75000 | 100000 | 100000 | 75000 | 75000 | 425000 | 100000 | 525000 | 5 | 26250 | 551250 | 475000 | 448750 | 1000000 | 1000000 | 8.875
ID | User Story | Description | Priority | Status | Estimation (Story Points) | Planned Sprint | Acceptance Criteria | Tasks | Dependencies | Risks | Notes
1 | User Login | Allow users to log in securely | High | Done | 5 | Sprint 1 | User can log in using email and password; proper error messages are shown. | Design UI, Implement authentication, Test login flow | None | Low | Requires UI review
2 | Dashboard Overview | Display summary of inventory and alerts | High | Done | 8 | Sprint 1 | Dashboard displays key metrics and alerts in real time. | Layout design, Data integration, UI testing | User Login must be complete | Medium | Waiting for design input
3 | Sell Medicine Feature | Record medicine sales with validation | High | Done | 8 | Sprint 2 | Sales can be recorded with proper validation and error handling. | Design sale form, Implement validation, Integrate with DB | Dashboard Overview | High | Confirmed with client
4 | Refill Stock Feature | Update stock levels and add new medicines | High | Done | 8 | Sprint 2 | Stock levels update correctly and new medicines are added. | Design stock update module, Develop refill logic, Testing | Sell Medicine Feature | Medium | Confirmed with client
5 | Low Stock Alerts | Automatically flag items below reorder level | Medium | Done | 8 | Sprint 3 | Alerts are triggered when stock falls below threshold. | Define thresholds, Implement alert mechanism, Test alerts | Refill Stock Feature | Low | Pending further discussion
6 | Reporting Module | Generate sales and inventory reports | Medium | Done | 8 | Sprint 4 | Reports are accurate and exportable in PDF/Excel. | Design report templates, Code report generation, Validate data | Dashboard Overview, Low Stock Alerts | High | Pending further discussion
7 | User Role Management | Implement role-based access control | Low | Done | 8 | Sprint 5 | Roles and permissions are configurable and secure. | Design role matrix, Implement RBAC logic, Test permissions | User Login | Medium | High priority follow-up needed
8 | Data Export | Export inventory data to CSV/Excel | Low | Done | 5 | Sprint 6 | Data exports correctly in chosen format. | Develop export functionality, Validate file format, User testing | Reporting Module | Low | Waiting for design input
9 | Performance Optimization | Improve application speed and scalability | Medium | Done | 8 | Sprint 7 | Application meets response time targets under load. | Profile application, Identify bottlenecks, Optimize code | Reporting Module, Data Export | High | Requires UI review
10 | User Training | Prepare training guides and documentation | Low | To Do | 5 | Sprint 8 | Training materials are complete and user-friendly. | Draft guides, Record training sessions, Compile documentation | All previous sprints | Low | High priority follow-up needed